## Sheet1
Story | Task | Estimate min (hr) | Estimate max (hr) | Actual | Comment
As a stakeholder evaluating the lab, I need a concise plan that outlines scope, assumptions, and risks with time estimates. This lets us validate priorities and de-risk before implementation. The deliverable is a brief plan and an estimate breakdown. | Project scoping, UX plan, and estimates | 0.5 | 1 | 1
As an experimenter, I need an API that accepts a prompt and parameter sets and returns model outputs reliably. It should handle retries/timeouts, expose helpful error messages, and provide endpoints to save/list/get/delete runs. This enables consistent generation and later analysis. | Backend API (generation, metrics, labs persistence) | 2 | 3 | 3.5
As a user, I want an interface to enter a prompt, configure multiple parameter sets, and compare responses with metrics and charts. It should be responsive, accessible, and efficient to explore variants. This helps me understand parameter trade-offs quickly. | Frontend UI (parameter controls, results, charts, history) | 2.5 | 3.5 | 4.5 | Had to redo the design a few times, wasn't happy with the inital versions
I need to integrate the frontend and the backend. As a user, I want clear feedback (rate limits, timeouts) and full control over persistence. | Integration of frontend and backend
As a maintainer, I need to manage the deployment for frontend/back-end | Deployment | 0.5 | 1 | 1